## Slide 1: Compiler Project Updates Mar 24th
Florida Institute of Cybersecurity Research Electrical and Computer Engineering Department
Arunabho Basu

## Slide 2: Progress at a glance
  Making decent progress, on track to meet first quarter deliverables
    Deliverables : 1) SRC first quarter report by April **
            **Need access to SRC project on pillar science website
  Detailed analysis of GCC compiler introduced vulnerability and its corresponding hardening
    How Branch Prediction Optimization makes code more vulnerable to LFI
    Our hardening against Branch Prediction Optimization at Compilation
  Shared reading materials with Mashahed and bringing him upto speed on the project
  Making the toolflow setup accessible to Pantha and Mashahed so we can work together

## Slide 3: Conditional Branch Hardening
  What happened during hardening ?
  - Faults modifying/bypassing branch condition will now directly lead to password checking failure instead of secret asset
  Harden
  Security Property : Default fall-through branch handles error rather than security asset

## Slide 4
  Dumped all internal states of compilation and studied how compilation takes place.
  $ riscv32-unknown-elf-gcc -fdump-tree-original password.c –c
  $ riscv32-unknown-elf-gcc -fdump-tree-gimple password.c –c
  $ riscv32-unknown-elf-gcc -fdump-tree-all password.c –c
  $ riscv32-unknown-elf-gcc -O2 -fdump-tree-cfg-graph -c password.c

## Slide 5
  Before and After Branch Prediction Optimization
  $ riscv32-unknown-elf-gcc -O2 -save-temps password.c -o password
  $ riscv32-unknown-elf-gcc -O1 -save-temps password.c -o password
  Branch Prediction Optimization switched the default branch
  Before
  After
  High level code had error in default branch (else)

## Slide 6: Branch Prediction Optimization
  How does this optimization help?
  Optimization : Hot Branch Instructions clustered together and pre-loaded into instruction cache pipeline so they can be readily fetched if condition is met
    If branch condition is met next instruction is already in pipeline (saves time)
    If branch condition is not met pipeline is flushed and cold branch is loaded (takes more time)
Branch Prediction Optimization
  Hot Branch
  Most likely taken branch based on analysis
  Cold Branch
  Less likely taken branch based on analysis

## Slide 7
Hot Branch
Cold Branch
Branch Condition
Instruction Cache Pipeline
  How does this optimization help?
  Optimization : Hot Branch Instructions clustered together and pre-loaded into instruction cache pipeline so they can be readily fetched if condition is met
    If branch condition is met next instruction is already in pipeline (saves time)
    If branch condition is not met pipeline is flushed and cold branch is loaded (takes more time)
Branch Prediction Optimization

## Slide 8
Access to Secret Asset (Hot Branch)
Error Handling (Cold Branch)
Branch Condition
Instruction Cache Pipeline
  How does this introduce Fault Injection Vulnerability ?
  - Faults modifying/bypassing branch condition will now directly lead to secret asset
Branch Prediction Optimization - Vulnerability

## Slide 9
  Vulnerability :
  Branch Predictor does not know if a branch has security asset and should be kept cold
  Branch Predictor decides hot (most likely) or cold (less likely) based on heuristic analysis
    Heuristic Analysis – detect error handling code, assign it cold always
Branch Prediction Optimization - Vulnerability
  Standard GCC compiler in default setting would always assign error handling branch as cold even if other branch has security asset

## Slide 10
  Hardening :
  Simple naïve solution : Turn off Branch Prediction Optimization
  Advanced solution : If there is a security asset, assign it always cold
    Static Branch Prediction Hint : __builtin_expect(branch condition, 0) - (this is what we implemented in our example)
    Profile guided Optimization (Dynamic) : Branch Prediction is guided by a profile containing branch weights (customizable)
Branch Prediction Optimization - Hardening
  Security Property Hardened : Default fall-through branch handles error rather than security asset

## Slide 11
  Evaluating the Hardening :
  Impact on performance – time taken and resources used measured before and after hardening
  Impact on Fault Injection Resilience – measured using SoFI before and after hardening
Next step – Evaluation of Hardening

## Slide 12
  Evaluating the Hardening :
  Impact on performance – time taken and resources used measured before and after hardening
    Time measured showed negligible overhead
    Possible reasons : short and lightweight program, maybe parallel processing was involved(?)
    Performance measured using perf : slightly increased cache-miss because now security asset needs to be loaded from cold branch
    Next step : evaluate other heavier programs
  Impact on Fault Injection Resilience – measured using SoFI before and after hardening
    Working with Pantha to troubleshoot SoFI
Next step – Evaluating Performance

## Slide 13: Next steps – Evaluating Fault Resiliency
  Input – Design File, Security Properties File, Fault List
  Output – Fault Assessment
  Analyze the waveforms to identify LFI target signals
  LFI Target list used to generate : - security properties and - hardening rules
  PicoRV32 CPU with test program loaded into memory
  Co-simulation using suitable Verilog simulator
SoFI Framework
  Quantified hardening analysis and report
  PicoRISC-V CPU
  Verilog softcore
  RV32i ISA
  Test program (for FIA)
  Runs on RISCV (written in C, compiled using riscv cross compiler)
  Compiled code converted to 32bit firmware in hex format

## Slide 14: The issues with SoFI
SoFI Framework
  Quantified fault resiliency report
  INPUT 2 : Critical Locations/Fault list
  Identifying critical locations from waveform analysis – local fault targeting our security property or global faults?
  INPUT 3 : Security Properties File
  Defining security property in a way SoFI can understand. Henian suggested editing his file but I am not sure if its working
  INPUT 1 : Design File
  Henian’s work show gate level netlist of design is accepted. Our RTL level design was synthesized to Gate level netlist.
  The synthesis process directly impacts the physical modelling of faults

## Slide 15: THANK YOU

## Slide 16: Current Framework
  PicoRISC-V CPU
  Verilog softcore
  RV32i ISA
  Test program (for FIA)
  Runs on RISCV (written in C, compiled using riscv cross compiler)
  Compiled code converted to 32bit firmware in hex format
  Firmware loaded on to memory of CPU core
  PicoRV32 CPU with test program loaded into memory

## Slide 17: Current Framework
  Input – Design File, Security Properties File, Fault List
  Output – Fault Assessment
  Analyze the waveforms to identify LFI target signals
  LFI Target list used to generate : - security properties and - hardening rules
  PicoRV32 CPU with test program loaded into memory
  Co-simulation using suitable Verilog simulator
SoFI Framework
  Quantified hardening analysis and report

## Slide 18: Current Roadblock
  Analyze the waveforms to identify LFI target signals
  PicoRV32 CPU with test program loaded into memory
  Co-simulation using suitable Verilog simulator

## Slide 19: Current Roadblock
  Analyze the waveforms to identify LFI target signals
  PicoRV32 CPU with test program loaded into memory
  Co-simulation using suitable Verilog simulator
Simulation using Iverilog
Simulation using VCS
vs
Example (using Hello World):

## Slide 20: Troubleshooting update
  What we know :
  VCS not cosimulating it correctly
  Not an issue with machine – same error reproduced on Henian’s machine
  Not an issue with test program code, all programs cosimulated on VCS giving erranous results while its working on iverilog
What we’re trying :
- Troubleshooting using error codes
- Checking VCS options from man page
- Modifying testbench
- Check other simulators
Simulation using Iverilog
Simulation using VCS
Another Example (using AES):

## Slide 21: Current Progress
Reading up on SoFI tool and how to use it
Researching FIA Vulnerability Analysis :
  Features/Characteristics that help in quantifying hardening
  Features that help in improving physical attack model
  Features whose impact can be augmented by compiler level hardening
Reading up on LFI and Physical Modeling

## Slide 22: Next Steps
Identifying Critical Instructions/Locations
Developing a framework that can identify critical instructions in code
Identifying hardening technique – replacement/addition/rewriting
  which gives positive change in hardening metrics,
  while keeping overhead low, and
  implementable during compilation stage

## Slide 23: Hardening example
Develop a GCC plugin that takes the non-hardened version and hardens it
Very similar approach to linting software
Required : Clear understanding of pre-processing stage and compilation stage of gcc-riscv32 compiler – how source code is translated to riscv instruction
Other hardening rules?

## Slide 24: Objective 1 – Compiler Toolchain
Architecture in use : RISC-V
Core in use : PicoRV32
GCC Cross-Compiler toolchain : gcc-riscv32-unknown-elf
Current Tasks :
  Getting familiar with RISC-V ISA and the GCC cross compiler toolchain
  Have started compiling simple programs to better understand pre-processing and compiling stage
  Goal is :
    Compile an AES program with a LFI vulnerable instruction
    Develop a plugin that hardens the said instruction

## Slide 25: Physical Fault Modelling
Existing GCC Options
Compile time Options
Run time Options
Control Flow Options
Stack Hardening
Function hardening
Jump statement hardening
Loop Hardening
Pointer Hardening
FI/SCA model vectors
FI
  Laser
  Clock
  Voltage
SCA
  EM Wave
  Power
  Time
Attacks which can be detected/prevented by these options

## Slide 26: Challenges in security Hardening
Hardening Toolflow :
  Identify and locate critical instructions, vulnerable to fault injection
  Harden the critical instruction
Going from C code to RV32i assembly code, locating critical instruction is not very straightforward
Pre-silicon vs Post-silicon
  RTL simulation cycle varies from actual hardware implementation cycle – making finding exact cycle even harder

## Slide 27: Security Hardening Example
Henian’s example of a simpler testcase: password authentication
  Call secret function under the correct key input
  What if “bnez a0, .L1” is skipped?
compile

## Slide 28: PicoRV32 Core
PicoRV32 is a Verilog softcore
Simulated on local machine and the compiled code is co-simulated on top of the softcore by inserting it into the memory of PicoRV32

## Slide 29: RISC-V compilation
Pre-processing
  Replaces macros and includes header files, resulting in a pure C source file with no preprocessor directives.
  riscv32-unknown-elf-gcc -E fics.c -o fics.i
Compilation
  Translates the preprocessed C code into assembly code for the RISC-V architecture
  riscv32-unknown-elf-gcc -S fics.i -o fics.s
Assembly
  Converts the assembly code into machine code, resulting in an object file
  riscv32-unknown-elf-as fics.s -o fics.o
Linking
  combines one or more object files (and any required libraries) into a final executable file
  riscv32-unknown-elf-gcc fics.o -o fics
GCC Cross Compiler
C Code
Compiled RV32i code

## Slide 30: Compiler Project Updates Feb 3rd
Florida Institute of Cybersecurity Research Electrical and Computer Engineering Department
Arunabho Basu

## Slide 31: Security Hardening Example
Example of a simple testcase: password authentication
  Call secret function under the correct key input
  What if “bne a0, zero, .L3” is skipped?
compile
  PC falls through to next sequential address which is the secret

## Slide 32: Security Hardening Example
harden
  What if “beq a0, zero, .L3” is skipped?
  PC can never reach branch L3 containing Secret Function

## Slide 33: High Level Analogy
Inequality Check
Equality Check
Same operation implemented in two ways :
  High level logic:
  If passwords don’t match
    Jump to Error
  Default (else) : Access Secret
  High level logic:
  If passwords match
    Jump to Access Secret
  Default (else) : Error

## Slide 34: Attacker’s Perspective
  Attacker’s Goal : Skip bne instruction
  Result : PC falls through to secret branch
  Attacker’s Goal : Make beq instruction always true
  Result : PC jumps to secret branch

## Slide 35: Primary LFI Target
Comparator Is a0 == 0 ?
Branch Target Address
Next Sequential Address
Final PC
MUX PC Decision
Final PC
Comparator Is a0 != 0 ?
Branch Target Address
Next Sequential Address
MUX PC Decision
Secret
Secret
Error
Error
Branch Condition
Branch Condition
OR
OR
a0
a0

## Slide 36: Other LFI Targets – Harder to Exploit
Register File: If the attacker can flip the value in a0 from nonzero to zero, then the branch condition changes. (Harder to flip because of small time window)
Instruction Decoder: A fault might corrupt the bne instruction opcode itself, turning it into a no-op or an always-jump. (Multiple Faults + Very hard to flip to target opcode)
Pipeline Latches/Flip-Flops: The pipeline stage registers store intermediate signals—if you flip the stored comparator result or the branch target PC, you can misdirect control flow. (Multiple Faults + Very hard to flip to target address)
PC Increment Logic: Even if the comparator is correct, messing with the final PC increment or branch addition could skip or misalign instructions. (Multiple Fault + Hard to locate)

## Slide 37: Quantifying Hardening
Hardening Metric = 2-1
Non-Hardened Assembly Code
FIA Vulnerability Analysis (1)
SoFI
Hardened Assembly Code
FIA Vulnerability Analysis (2)
SoFI

## Slide 38: SoFi Fault Analysis – Current Progress and Challenges
Current Progress – Troubleshooting SoFI RTL Implementation
SoFI Input :
  RTL Design File –
    Co-simulation of softcore RISC-V and non hardened program executable
    Generates VCD file of simulation from VCS
    Challenge – Timing and memory mapping the co-simulation
  Stimulus VCD File –
    ZO1X simulation to find faults that violate SP
  Security Property File (Strobe File) –
    No instruction skipping
    Challenge – Locating the fault cycle

## Slide 39: SRC Proposal Deliverables and Timeline
Quarter 1-3 : SPICE-level and layout-level modeling of the physical characteristics of fault injection and side-channel attacks
Quarter 4 : Post-silicon attack test on chip/SoC, perform vulnerability analysis of software executions, and improve the attack models.
Quarter 1 : Investigation and development of physically-aware hardening techniques
Quarter 2 : Developing executable security properties and LUT/ML-based model interfaces to guide hardening strategies.
Quarter 3-4 : Integration of hardening techniques into software compilation in the form of GCC plug-in/LLVM/Clang
Quarter 1-2 : Extensive validation of the PASS flow on FPGA platform with iterative test of hardened software compilations
Quarter 3-4 : Broadening the attack scenarios by including more security properties, and fine-tuning of physical attack models.
Year 1
Year 2
Year 3

## Slide 40: SRC Proposal Deliverables – Year 1 (2025)
Qtr 1
Qtr 2
Qtr 3
Qtr 4
FIA Modeling : SPICE Level
FIA Modeling : Layout Level
SCA Modeling : SPICE Level
SCA Modeling : Layout Level
Post Silicon Attack Test
Vulnerability Analysis of Software Execution
Improve Attack Models

## Slide 41: SRC Proposal Deliverables – Quarter 1 (March 2025)
Qtr 1
Fault Injection Modeling – SPICE Level
Set up RTL design files
Set up Testbench
Run Transient simulations
Model and inject fault during transient simulations
Harden and repeat last step
Evaluate difference between before and after

## Slide 42: THANK YOU